## Plan
Plan ID | Plan name | Date of export
xTo6p4Kohk-KXWnZQN7h8ckAEuD- | R26-IT-066 | 2026-10-14

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
zjXn-TM3LU-q1owf-VZhvskAHShN | Finalize the NPK Sensors | To do |  | Completed | Medium | KARALLIYADDA K K U B M U B it22178718 | KARALLIYADDA K K U B M U B it22178718 | 2026-05-03 | 2026-05-05 |  |  | false | 2026-05-05 | KARALLIYADDA K K U B M U B it22178718
LvVfmcDV_EqJGqXYVDaMHckALgfu | Final testing of Data Model Training | To do |  | Not started | Important | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-05-24 | 2026-05-17 |  | true | [5 empty] | Only foud from ag office. waiting for confirmation from rrdi
hhU8XwWw1UqLa1lOXSe4-skAJoXS | Final testing of Data Model Training | To do |  | Completed | Important | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | HARSHIKA M A B it22261632 | 2026-10-14 | 2026-05-23 | 2026-05-16 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
8YZhpXq63k6A7IpJG-OAG8kAFNOM | Final testing of Data Model Training | To do |  | Completed | Important | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | HARSHIKA M A B it22261632 | 2026-10-14 | 2026-05-22 | 2026-05-15 |  | false | 2026-10-14 | HARSHIKA M A B it22261632 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
8neRdhANp0i_gwejsQQQTMkAOGLf | Final testing of Data Model Training | To do |  | Completed | Important | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | HARSHIKA M A B it22261632 | 2026-10-14 | 2026-05-21 | 2026-05-14 |  | false | 2026-10-14 | HARSHIKA M A B it22261632 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
xWkMcx5IoUu5jj_iQlFh0skAJfGV | Final testing of Data Model Training | To do |  | Completed | Important | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | HARSHIKA M A B it22261632 | 2026-10-14 | 2026-05-20 | 2026-05-13 |  | false | 2026-10-14 | HARSHIKA M A B it22261632 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
sO1ts3roIE2N4SNHDnm2wckAMfLT | Final testing of Data Model Training | To do |  | Completed | Important | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | WEERASINGHE W A H V it22266446 | 2026-10-14 | 2026-05-19 | 2026-05-12 |  | false | 2026-10-14 | HARSHIKA M A B it22261632 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
kMVkFyArFUWkwm3FVgFVMckAFYJz | Final testing of Data Model Training | To do |  | Completed | Important | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | WEERASINGHE W A H V it22266446 | 2026-10-14 | 2026-05-18 | 2026-05-11 |  | false | 2026-10-14 | HARSHIKA M A B it22261632 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
YKSCO7CzlESnqOQVC28AOckALtOU | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-05-17 | 2026-05-10 |  | false | 2026-10-14 | WEERASINGHE W A H V it22266446 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
yVA8CyF8zUS6UY8IZi0HJ8kAOz8d | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-05-16 | 2026-05-09 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
XLwiMPyjg0e4M0Gd2IQXb8kAP1IT | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-05-15 | 2026-05-08 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
gyij-njgfEeKvbsRMEGs0MkACjGe | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | Bandara R.M.A.S it21811104 | 2026-08-26 | 2026-05-14 | 2026-05-07 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
s17kt3_A60SiEB7RvKHeKMkAGn85 | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | Bandara R.M.A.S it21811104 | 2026-08-26 | 2026-05-13 | 2026-05-06 |  | false | 2026-08-26 | Bandara R.M.A.S it21811104 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
k-uZ_gTNPEyl-axDU4IGmskAJFhA | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | Bandara R.M.A.S it21811104 | 2026-08-26 | 2026-05-12 | 2026-05-05 |  | false | 2026-08-26 | Bandara R.M.A.S it21811104 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
cSG0-Npm9UumfDFQEolS2skAMlq6 | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | Bandara R.M.A.S it21811104 | 2026-08-26 | 2026-05-11 | 2026-05-04 |  | false | 2026-08-26 | Bandara R.M.A.S it21811104 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
wLtYKWsc506Nn4mUj85dJMkAADC3 | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-05-10 | 2026-05-03 |  | false | 2026-08-26 | Bandara R.M.A.S it21811104 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
-hDhh9LXWEONg26P__tdEckAIKbX | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-05-09 | 2026-05-02 |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
yXkjkPX7GkWDgZWGJvN4s8kACmZV | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-05-08 | 2026-05-01 |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
mIIR0DnFxkOLpGF2nDGrFskAGLJE | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-05-14 | 2026-05-07 | 2026-04-30 |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
DtOilTgIV0-YiyIfZoonZckAGg8z | Final testing of Data Model Training | To do |  | Completed | Urgent | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-05-03 | 2026-05-07 | 2026-04-30 |  | false | 2026-05-14 | KARALLIYADDA K K U B M U B it22178718 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
MoJZmWa8PUCEM7F627J3JckAElu9 | Set up the Flutter PWA project structure, establish folder architecture, environment configuration, and GitHub branching workflow for the project. | To do |  | Completed | Medium | KARALLIYADDA K K U B M U B it22178718 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-10 |  |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718
GpR441dFV0ifCiV9z_APHckAAbwh | Define the datdatabase schema and API requirements for the Crop Selection component, including required input/outpabase schema and API requirements for the Crop Selection component, including required input/output fields and prediction response structure. | To do |  | Completed | Medium | Bandara R.M.A.S it21811104 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-10 |  |  | false | 2026-08-26 | Bandara R.M.A.S it21811104
__dbjg0hyU-gpvYs_89ct8kALLSM | Initial Flutter UI flow for crop selection, including input forms, validation, and result display screens. | To do |  | Completed | Medium | Bandara R.M.A.S it21811104 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-14 |  |  | false | 2026-08-26 | Bandara R.M.A.S it21811104
7mLAbS8n50-6GEhKtkKCnckAHYs4 | Design and implement the database structure and backend API endpoints required for the Fertilization Selection component. | To do |  | Completed | Medium | KARALLIYADDA K K U B M U B it22178718 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-14 |  |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718
A6_04jzNM0aNoKKp7uywTMkACp4W | Connecting the Crop Selection Flutter interface with its backend API and handle API responses, errors, and loading states. | To do |  | Completed | Medium | Bandara R.M.A.S it21811104 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-18 |  |  | false | 2026-08-26 | Bandara R.M.A.S it21811104
TQj6Jr01JUuDe_b3oYpdd8kANdwK | Flutter UI for Fertilization Selection and integrate the required user input fields with backend communication. | To do |  | Completed | Medium | KARALLIYADDA K K U B M U B it22178718 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-19 |  |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718
k7xnt1BIfE-Jkuyt9mZi-8kAKmih | Backend and database integration for the Disease Detection component, including image upload handling | To do |  | Completed | Medium | HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-22 |  |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
5LhF-jyhsE63zkLFYvALdckAAH-J | Define the required data fields, database tables, and API flow for Harvest Estimation based on field and crop information. | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-24 | 2026-07-11 |  | false | 2026-08-26 | WEERASINGHE W A H V it22266446
bWzGdnYxAUW3tWNZPfzKD8kABsEt | Image functionality in Flutter and connect the Disease Detection interface with its backend | To do |  | Completed | Medium | HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-26 |  |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
Y43n0LNsW0Ga_8y6qQBJQskAELBp | Harvest Estimation user interface and implement API integration for submitting field data and displaying estimation results | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-26 |  |  | false | 2026-08-26 | WEERASINGHE W A H V it22266446
ekauYqVvNU2vgeN98ib_hMkANJ2Q | Connection testing for IoT device with fertilization and crop selection components | To do |  | Completed | Medium | Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-07-30 |  |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718
B9rTiC1fqk-MaJS7Z-yR38kAGmYH | Push your changes to individual branches, PR and solve merge conflicts | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-08-01 |  |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718
74733TlR_Uahzjg9MdkMEskAHmsV | Connecting IoT device with backend and database | To do |  | Completed | Medium | KARALLIYADDA K K U B M U B it22178718 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-08-05 |  |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718
oYzfxhG6Ak2MhC5vUfsZ7MkAOQ-U | Ensure user flow consistency among 4 components | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-08-12 |  |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718
g9-T9j3Pk0SDACK8NIaMj8kAK0q1 | Component level testing | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-08-16 |  |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
89GceFlPYUysJF2HZIsvd8kANzR_ | Test IoT-to-backend-to-PWA data flow using sample sensor/device data and verify data consistency across the system | To do |  | Completed | Medium | Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-08-20 |  |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718
8srhK_7XxUmV5ObvseRnZMkABvTv | Conduct full system testing | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 |  |  |  | false | 2026-08-26 | KARALLIYADDA K K U B M U B it22178718
Fxb60sdQokKO-1t0w03E-skAIECw | pp2 presentation completion | To do |  | Not started | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-30 | 2026-09-28 |  | true
UtagsVaU2Uad2RZbjn0qn8kAHxPv | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-29 | 2026-09-27 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
eGCMbLV3PkCTmKpbhizuIMkABc51 | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | HARSHIKA M A B it22261632 | 2026-10-14 | 2026-09-28 | 2026-09-26 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
P9VjmJkWVUGlrUNRO72dlskAFQFt | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | HARSHIKA M A B it22261632 | 2026-10-14 | 2026-09-27 | 2026-09-25 |  | false | 2026-10-14 | HARSHIKA M A B it22261632
KF4IIRcQK0CffScuCzx3ickALhFK | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | HARSHIKA M A B it22261632 | 2026-10-14 | 2026-09-26 | 2026-09-24 |  | false | 2026-10-14 | HARSHIKA M A B it22261632
s932VgQR30-h7Q9Sl52FCckAG4ck | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | HARSHIKA M A B it22261632 | 2026-10-14 | 2026-09-25 | 2026-09-23 |  | false | 2026-10-14 | HARSHIKA M A B it22261632
SzHsd2GEPUeU7ycWFB2CJckACblO | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | HARSHIKA M A B it22261632 | 2026-10-14 | 2026-09-24 | 2026-09-22 |  | false | 2026-10-14 | HARSHIKA M A B it22261632
JLIcXzti80yM7A1nKieqX8kAHBav | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | WEERASINGHE W A H V it22266446 | 2026-10-14 | 2026-09-23 | 2026-09-21 |  | false | 2026-10-14 | HARSHIKA M A B it22261632
Bx5FlcbviEady0abpG1qSckAFFVq | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | WEERASINGHE W A H V it22266446 | 2026-10-14 | 2026-09-22 | 2026-09-20 |  | false | 2026-10-14 | WEERASINGHE W A H V it22266446
t4cS2x79IUqxMlZpyNhkhckADPis | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | WEERASINGHE W A H V it22266446 | 2026-10-14 | 2026-09-21 | 2026-09-19 |  | false | 2026-10-14 | WEERASINGHE W A H V it22266446
iGAs-3JwSE-ghYBL96yKdMkAKIyx | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | WEERASINGHE W A H V it22266446 | 2026-10-14 | 2026-09-20 | 2026-09-18 |  | false | 2026-10-14 | WEERASINGHE W A H V it22266446
zQv9ujUttUeattiBYEkq6skAHYcJ | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | HARSHIKA M A B it22261632 | 2026-10-14 | 2026-09-19 | 2026-09-17 |  | false | 2026-10-14 | WEERASINGHE W A H V it22266446
s4mcycSZn0i6VcnfFwKO58kAHYiR | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | WEERASINGHE W A H V it22266446 | 2026-10-14 | 2026-09-18 | 2026-09-16 |  | false | 2026-10-14 | HARSHIKA M A B it22261632
_8qdcItUrUWVlbOS0BXiB8kAFeB_ | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | WEERASINGHE W A H V it22266446 | 2026-10-14 | 2026-09-17 | 2026-09-15 |  | false | 2026-10-14 | WEERASINGHE W A H V it22266446
k-qM2x_8uEWPfzbHoiXUZskAMSJz | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | WEERASINGHE W A H V it22266446 | 2026-10-14 | 2026-09-16 | 2026-09-14 |  | false | 2026-10-14 | WEERASINGHE W A H V it22266446
s-iSR1i4f0GpQMylSVV1HckAHFOP | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | WEERASINGHE W A H V it22266446 | 2026-10-14 | 2026-09-15 | 2026-09-13 |  | false | 2026-10-14 | WEERASINGHE W A H V it22266446
_9R1UWD2ykCmHfo3wFV9SskAD9F9 | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-14 | 2026-09-12 |  | false | 2026-10-14 | WEERASINGHE W A H V it22266446
4UBZZZCSTUiuw12aQn-0j8kAPYfo | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-13 | 2026-09-11 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
Yy4269Qx0kKWF8IepM11y8kALp67 | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-12 | 2026-09-10 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
KWLTyePvTU6urmK7rNSi8skAOHeE | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-11 | 2026-09-09 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
ChuKEALufUKtOtaiwEDRRMkAIOkD | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-10 | 2026-09-08 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
JKDfxHSpDU6oDf3z1oGje8kAAeCg | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-09 | 2026-09-07 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
2t-Mc47Ld0ixx573XvAQ6MkAK6gu | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-08 | 2026-09-06 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
vdTGTmcOQkKgDO074tAr8MkADUg6 | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-07 | 2026-09-05 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
l5LBBC0nhE-HGe8IuZza8skAAu3- | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-06 | 2026-09-04 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
YngQ8eHn206FtNpefGYHz8kAFxBs | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-05 | 2026-09-03 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
CVnFziobvEWtKnVX9T3YeskABwE- | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-04 | 2026-09-02 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
5DC_g69_7ki7szGd3RSI5skAD32L | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-03 | 2026-09-01 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
UcHz1uiuYkqvCWzofR3p8ckANYBQ | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-02 | 2026-08-31 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
z2kJTkrFVEyYvkE9JnRJM8kAEi1f | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-09-01 | 2026-08-30 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
Zj_5n9KDs020aiDeFzI_CMkAEuYy | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-08-31 | 2026-08-29 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
LHtGXDfSokyQWaxl7BOtCskACtCg | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-08-30 | 2026-08-28 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
kY5PvKooCki1AXevz4o5GckAG6_1 | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-08-29 | 2026-08-27 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
zwKDqRXSo0OiYS-i8SzysckAKoHf | pp2 presentation completion | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-08-28 | 2026-08-26 |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718
baaW06lODkiAn0eqF0lWtMkAGAQZ | Shot the demo video in case app does not work in pp2 | To do |  | Completed | Medium | WEERASINGHE W A H V it22266446;Bandara R.M.A.S it21811104;KARALLIYADDA K K U B M U B it22178718;HARSHIKA M A B it22261632 | KARALLIYADDA K K U B M U B it22178718 | 2026-08-26 | 2026-08-30 | 2026-08-26 |  | false | 2026-08-26 | WEERASINGHE W A H V it22266446
jm_C4Z_tP0q4WVO5IF6JuMkAILVw | Individual Thesis Upload | To do |  | Completed | Medium |  | KARALLIYADDA K K U B M U B it22178718 | 2026-10-14 | 2026-10-13 |  |  | false | 2026-10-14 | KARALLIYADDA K K U B M U B it22178718

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
zjXn-TM3LU-q1owf-VZhvskAHShN | Finalize the NPK Sensors | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 744bb6e0-699a-479c-960e-9ef847c2c599 | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-05-03 | 2026-05-05 |  |  | false | 2026-05-05 | 744bb6e0-699a-479c-960e-9ef847c2c599
LvVfmcDV_EqJGqXYVDaMHckALgfu | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Not started | Important | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-05-24 | 2026-05-17 |  | true | [5 empty] | Only foud from ag office. waiting for confirmation from rrdi
hhU8XwWw1UqLa1lOXSe4-skAJoXS | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Important | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | e7cddb95-e82e-440b-968b-1d8e7084e6db | 2026-10-14 | 2026-05-23 | 2026-05-16 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
8YZhpXq63k6A7IpJG-OAG8kAFNOM | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Important | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | e7cddb95-e82e-440b-968b-1d8e7084e6db | 2026-10-14 | 2026-05-22 | 2026-05-15 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
8neRdhANp0i_gwejsQQQTMkAOGLf | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Important | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | e7cddb95-e82e-440b-968b-1d8e7084e6db | 2026-10-14 | 2026-05-21 | 2026-05-14 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
xWkMcx5IoUu5jj_iQlFh0skAJfGV | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Important | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | e7cddb95-e82e-440b-968b-1d8e7084e6db | 2026-10-14 | 2026-05-20 | 2026-05-13 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
sO1ts3roIE2N4SNHDnm2wckAMfLT | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Important | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 697e2fef-d694-44d0-bba3-02b25e29502d | 2026-10-14 | 2026-05-19 | 2026-05-12 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
kMVkFyArFUWkwm3FVgFVMckAFYJz | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Important | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 697e2fef-d694-44d0-bba3-02b25e29502d | 2026-10-14 | 2026-05-18 | 2026-05-11 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
YKSCO7CzlESnqOQVC28AOckALtOU | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-05-17 | 2026-05-10 |  | false | 2026-10-14 | 697e2fef-d694-44d0-bba3-02b25e29502d |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
yVA8CyF8zUS6UY8IZi0HJ8kAOz8d | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-05-16 | 2026-05-09 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
XLwiMPyjg0e4M0Gd2IQXb8kAP1IT | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-05-15 | 2026-05-08 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
gyij-njgfEeKvbsRMEGs0MkACjGe | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 179ecaa7-abab-4727-a847-bb29db99bc11 | 2026-08-26 | 2026-05-14 | 2026-05-07 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
s17kt3_A60SiEB7RvKHeKMkAGn85 | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 179ecaa7-abab-4727-a847-bb29db99bc11 | 2026-08-26 | 2026-05-13 | 2026-05-06 |  | false | 2026-08-26 | 179ecaa7-abab-4727-a847-bb29db99bc11 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
k-uZ_gTNPEyl-axDU4IGmskAJFhA | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 179ecaa7-abab-4727-a847-bb29db99bc11 | 2026-08-26 | 2026-05-12 | 2026-05-05 |  | false | 2026-08-26 | 179ecaa7-abab-4727-a847-bb29db99bc11 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
cSG0-Npm9UumfDFQEolS2skAMlq6 | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 179ecaa7-abab-4727-a847-bb29db99bc11 | 2026-08-26 | 2026-05-11 | 2026-05-04 |  | false | 2026-08-26 | 179ecaa7-abab-4727-a847-bb29db99bc11 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
wLtYKWsc506Nn4mUj85dJMkAADC3 | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-05-10 | 2026-05-03 |  | false | 2026-08-26 | 179ecaa7-abab-4727-a847-bb29db99bc11 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
-hDhh9LXWEONg26P__tdEckAIKbX | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-05-09 | 2026-05-02 |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
yXkjkPX7GkWDgZWGJvN4s8kACmZV | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-05-08 | 2026-05-01 |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
mIIR0DnFxkOLpGF2nDGrFskAGLJE | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-05-14 | 2026-05-07 | 2026-04-30 |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
DtOilTgIV0-YiyIfZoonZckAGg8z | Final testing of Data Model Training | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Urgent | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-05-03 | 2026-05-07 | 2026-04-30 |  | false | 2026-05-14 | 744bb6e0-699a-479c-960e-9ef847c2c599 |  |  |  | Only foud from ag office. waiting for confirmation from rrdi
MoJZmWa8PUCEM7F627J3JckAElu9 | Set up the Flutter PWA project structure, establish folder architecture, environment configuration, and GitHub branching workflow for the project. | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 744bb6e0-699a-479c-960e-9ef847c2c599 | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-10 |  |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599
GpR441dFV0ifCiV9z_APHckAAbwh | Define the datdatabase schema and API requirements for the Crop Selection component, including required input/outpabase schema and API requirements for the Crop Selection component, including required input/output fields and prediction response structure. | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 179ecaa7-abab-4727-a847-bb29db99bc11 | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-10 |  |  | false | 2026-08-26 | 179ecaa7-abab-4727-a847-bb29db99bc11
__dbjg0hyU-gpvYs_89ct8kALLSM | Initial Flutter UI flow for crop selection, including input forms, validation, and result display screens. | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 179ecaa7-abab-4727-a847-bb29db99bc11 | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-14 |  |  | false | 2026-08-26 | 179ecaa7-abab-4727-a847-bb29db99bc11
7mLAbS8n50-6GEhKtkKCnckAHYs4 | Design and implement the database structure and backend API endpoints required for the Fertilization Selection component. | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 744bb6e0-699a-479c-960e-9ef847c2c599 | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-14 |  |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599
A6_04jzNM0aNoKKp7uywTMkACp4W | Connecting the Crop Selection Flutter interface with its backend API and handle API responses, errors, and loading states. | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 179ecaa7-abab-4727-a847-bb29db99bc11 | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-18 |  |  | false | 2026-08-26 | 179ecaa7-abab-4727-a847-bb29db99bc11
TQj6Jr01JUuDe_b3oYpdd8kANdwK | Flutter UI for Fertilization Selection and integrate the required user input fields with backend communication. | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 744bb6e0-699a-479c-960e-9ef847c2c599 | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-19 |  |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599
k7xnt1BIfE-Jkuyt9mZi-8kAKmih | Backend and database integration for the Disease Detection component, including image upload handling | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-22 |  |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
5LhF-jyhsE63zkLFYvALdckAAH-J | Define the required data fields, database tables, and API flow for Harvest Estimation based on field and crop information. | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-24 | 2026-07-11 |  | false | 2026-08-26 | 697e2fef-d694-44d0-bba3-02b25e29502d
bWzGdnYxAUW3tWNZPfzKD8kABsEt | Image functionality in Flutter and connect the Disease Detection interface with its backend | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-26 |  |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
Y43n0LNsW0Ga_8y6qQBJQskAELBp | Harvest Estimation user interface and implement API integration for submitting field data and displaying estimation results | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-26 |  |  | false | 2026-08-26 | 697e2fef-d694-44d0-bba3-02b25e29502d
ekauYqVvNU2vgeN98ib_hMkANJ2Q | Connection testing for IoT device with fertilization and crop selection components | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599 | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-07-30 |  |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599
B9rTiC1fqk-MaJS7Z-yR38kAGmYH | Push your changes to individual branches, PR and solve merge conflicts | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-08-01 |  |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599
74733TlR_Uahzjg9MdkMEskAHmsV | Connecting IoT device with backend and database | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 744bb6e0-699a-479c-960e-9ef847c2c599 | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-08-05 |  |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599
oYzfxhG6Ak2MhC5vUfsZ7MkAOQ-U | Ensure user flow consistency among 4 components | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-08-12 |  |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599
g9-T9j3Pk0SDACK8NIaMj8kAK0q1 | Component level testing | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-08-16 |  |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
89GceFlPYUysJF2HZIsvd8kANzR_ | Test IoT-to-backend-to-PWA data flow using sample sensor/device data and verify data consistency across the system | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599 | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-08-20 |  |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599
8srhK_7XxUmV5ObvseRnZMkABvTv | Conduct full system testing | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 |  |  |  | false | 2026-08-26 | 744bb6e0-699a-479c-960e-9ef847c2c599
Fxb60sdQokKO-1t0w03E-skAIECw | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Not started | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-30 | 2026-09-28 |  | true
UtagsVaU2Uad2RZbjn0qn8kAHxPv | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-29 | 2026-09-27 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
eGCMbLV3PkCTmKpbhizuIMkABc51 | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | e7cddb95-e82e-440b-968b-1d8e7084e6db | 2026-10-14 | 2026-09-28 | 2026-09-26 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
P9VjmJkWVUGlrUNRO72dlskAFQFt | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | e7cddb95-e82e-440b-968b-1d8e7084e6db | 2026-10-14 | 2026-09-27 | 2026-09-25 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db
KF4IIRcQK0CffScuCzx3ickALhFK | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | e7cddb95-e82e-440b-968b-1d8e7084e6db | 2026-10-14 | 2026-09-26 | 2026-09-24 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db
s932VgQR30-h7Q9Sl52FCckAG4ck | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | e7cddb95-e82e-440b-968b-1d8e7084e6db | 2026-10-14 | 2026-09-25 | 2026-09-23 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db
SzHsd2GEPUeU7ycWFB2CJckACblO | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | e7cddb95-e82e-440b-968b-1d8e7084e6db | 2026-10-14 | 2026-09-24 | 2026-09-22 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db
JLIcXzti80yM7A1nKieqX8kAHBav | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 697e2fef-d694-44d0-bba3-02b25e29502d | 2026-10-14 | 2026-09-23 | 2026-09-21 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db
Bx5FlcbviEady0abpG1qSckAFFVq | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 697e2fef-d694-44d0-bba3-02b25e29502d | 2026-10-14 | 2026-09-22 | 2026-09-20 |  | false | 2026-10-14 | 697e2fef-d694-44d0-bba3-02b25e29502d
t4cS2x79IUqxMlZpyNhkhckADPis | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 697e2fef-d694-44d0-bba3-02b25e29502d | 2026-10-14 | 2026-09-21 | 2026-09-19 |  | false | 2026-10-14 | 697e2fef-d694-44d0-bba3-02b25e29502d
iGAs-3JwSE-ghYBL96yKdMkAKIyx | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 697e2fef-d694-44d0-bba3-02b25e29502d | 2026-10-14 | 2026-09-20 | 2026-09-18 |  | false | 2026-10-14 | 697e2fef-d694-44d0-bba3-02b25e29502d
zQv9ujUttUeattiBYEkq6skAHYcJ | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | e7cddb95-e82e-440b-968b-1d8e7084e6db | 2026-10-14 | 2026-09-19 | 2026-09-17 |  | false | 2026-10-14 | 697e2fef-d694-44d0-bba3-02b25e29502d
s4mcycSZn0i6VcnfFwKO58kAHYiR | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 697e2fef-d694-44d0-bba3-02b25e29502d | 2026-10-14 | 2026-09-18 | 2026-09-16 |  | false | 2026-10-14 | e7cddb95-e82e-440b-968b-1d8e7084e6db
_8qdcItUrUWVlbOS0BXiB8kAFeB_ | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 697e2fef-d694-44d0-bba3-02b25e29502d | 2026-10-14 | 2026-09-17 | 2026-09-15 |  | false | 2026-10-14 | 697e2fef-d694-44d0-bba3-02b25e29502d
k-qM2x_8uEWPfzbHoiXUZskAMSJz | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 697e2fef-d694-44d0-bba3-02b25e29502d | 2026-10-14 | 2026-09-16 | 2026-09-14 |  | false | 2026-10-14 | 697e2fef-d694-44d0-bba3-02b25e29502d
s-iSR1i4f0GpQMylSVV1HckAHFOP | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 697e2fef-d694-44d0-bba3-02b25e29502d | 2026-10-14 | 2026-09-15 | 2026-09-13 |  | false | 2026-10-14 | 697e2fef-d694-44d0-bba3-02b25e29502d
_9R1UWD2ykCmHfo3wFV9SskAD9F9 | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-14 | 2026-09-12 |  | false | 2026-10-14 | 697e2fef-d694-44d0-bba3-02b25e29502d
4UBZZZCSTUiuw12aQn-0j8kAPYfo | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-13 | 2026-09-11 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
Yy4269Qx0kKWF8IepM11y8kALp67 | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-12 | 2026-09-10 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
KWLTyePvTU6urmK7rNSi8skAOHeE | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-11 | 2026-09-09 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
ChuKEALufUKtOtaiwEDRRMkAIOkD | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-10 | 2026-09-08 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
JKDfxHSpDU6oDf3z1oGje8kAAeCg | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-09 | 2026-09-07 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
2t-Mc47Ld0ixx573XvAQ6MkAK6gu | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-08 | 2026-09-06 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
vdTGTmcOQkKgDO074tAr8MkADUg6 | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-07 | 2026-09-05 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
l5LBBC0nhE-HGe8IuZza8skAAu3- | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-06 | 2026-09-04 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
YngQ8eHn206FtNpefGYHz8kAFxBs | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-05 | 2026-09-03 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
CVnFziobvEWtKnVX9T3YeskABwE- | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-04 | 2026-09-02 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
5DC_g69_7ki7szGd3RSI5skAD32L | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-03 | 2026-09-01 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
UcHz1uiuYkqvCWzofR3p8ckANYBQ | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-02 | 2026-08-31 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
z2kJTkrFVEyYvkE9JnRJM8kAEi1f | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-09-01 | 2026-08-30 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
Zj_5n9KDs020aiDeFzI_CMkAEuYy | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-08-31 | 2026-08-29 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
LHtGXDfSokyQWaxl7BOtCskACtCg | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-08-30 | 2026-08-28 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
kY5PvKooCki1AXevz4o5GckAG6_1 | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-08-29 | 2026-08-27 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
zwKDqRXSo0OiYS-i8SzysckAKoHf | pp2 presentation completion | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-08-28 | 2026-08-26 |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599
baaW06lODkiAn0eqF0lWtMkAGAQZ | Shot the demo video in case app does not work in pp2 | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium | 697e2fef-d694-44d0-bba3-02b25e29502d;179ecaa7-abab-4727-a847-bb29db99bc11;744bb6e0-699a-479c-960e-9ef847c2c599;e7cddb95-e82e-440b-968b-1d8e7084e6db | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-08-26 | 2026-08-30 | 2026-08-26 |  | false | 2026-08-26 | 697e2fef-d694-44d0-bba3-02b25e29502d
jm_C4Z_tP0q4WVO5IF6JuMkAILVw | Individual Thesis Upload | ADGtd1hiTkGec0RXsiV9IckALpk4 |  | Completed | Medium |  | 744bb6e0-699a-479c-960e-9ef847c2c599 | 2026-10-14 | 2026-10-13 |  |  | false | 2026-10-14 | 744bb6e0-699a-479c-960e-9ef847c2c599

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
ADGtd1hiTkGec0RXsiV9IckALpk4 | To do

## Users
User ID | User Name | Email
744bb6e0-699a-479c-960e-9ef847c2c599 | KARALLIYADDA K K U B M U B it22178718 | it22178718@my.sliit.lk
697e2fef-d694-44d0-bba3-02b25e29502d | WEERASINGHE W A H V it22266446 | it22266446@my.sliit.lk
179ecaa7-abab-4727-a847-bb29db99bc11 | Bandara R.M.A.S it21811104 | it21811104@my.sliit.lk
e7cddb95-e82e-440b-968b-1d8e7084e6db | HARSHIKA M A B it22261632 | it22261632@my.sliit.lk